## Seeram Govindan
To-do list
To be completed by: |  |  |  | Name Seeram Govindan
Deadline: |  |  |  | Date 12/14/25
Project 4
% done | Phase | Start By | Original Due By | Revise due by | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-03 |  | 1 day
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-01 | 2025-12-03 |  | 1 day
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03 |  | 1 day
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Create tables | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Load all production tables | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Final Recording | 2025-12-14 | 2025-12-16 |  | .5 day

## Hasan Husseini
To-do list
To be completed by: |  |  |  | Hasan Husseini
Deadline: |  |  |  | 2025-12-16
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-02 | 2025-12-02 | 1 day
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-02 | 2025-12-03 | 2025-12-03 | 1 day
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03 | 2025-12-03 | 1 day
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Create tables | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Load all production tables | 2025-12-14 | 2025-12-15 | 2025-12-14 | <1 day
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15 | 2025-12-14 | <1 day
100% | Final Recording | 2025-12-14 | 2025-12-15 | 2025-12-16 | .5 day

## Giorgos Stefanis
To-do list
To be completed by: |  | Giorgos Stefanis |  | Name Giorgos Stefanis
Deadline: |  | 2025-12-16 |  | Date
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-03
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-01 | 2025-12-03
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13
100% | Create tables | 2025-12-12 | 2025-12-23
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13
100% | Load all production tables | 2025-12-14 | 2025-12-15
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15
100% | Final Recording | 2025-12-14 | 2025-12-16

## Ridhwan Ibrahim
To-do list
To be completed by: |  |  |  | Name: Ridhwan Ibrahim
Deadline: |  | 2025-12-14 |  | Date 12/14/25
Project 4
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-02 | 2025-12-02 | 1 day
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-02 | 2025-12-03 | 2025-12-03 | 1 day
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03 | 2025-12-03 | 1 day
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Create tables | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13 | 2025-12-13 | 1.5 days
100% | Load all production tables | 2025-12-14 | 2025-12-15 | 2025-12-14 | <1 day
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15 | 2025-12-14 | <1 day
100% | Final Recording | 2025-12-14 | 2025-12-15 | 2025-12-16 | .5 day

## Youlun Wang
To-do list
To be completed by: |  |  |  | Name: Youlun Wang
Deadline: |  |  |  | Date 12/14/25
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-03 |  | 1 day
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-01 | 2025-12-03 |  | 1 day
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03 |  | 1 day
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Create tables | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13 |  | 1.5 days
100% | Load all production tables | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Final Recording | 2025-12-14 | 2025-12-16 |  | .5 day

## Michael Cipriani
To-do list
To be completed by: |  |  |  | Name Michael Cipriani
Deadline: |  |  |  | Date 12/14/25
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting to Analyze Source Table | 2025-12-01 | 2025-12-03 |  | 2 days
100% | Meeting to Identify Entites, Attributes and Relationships and Normalize to 3NF | 2025-12-01 | 2025-12-03 |  | 2 days
100% | Start Modeling ERD diagram | 2025-12-02 | 2025-12-03 |  | 1 day
100% | Finalize Schemas and UDTs | 2025-12-12 | 2025-12-13 |  | 1 day
100% | Create tables | 2025-12-12 | 2025-12-13 |  | 1 day
100% | Create ETL stored procedures to load tables | 2025-12-12 | 2025-12-13 |  | 1 day
100% | Load all production tables | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Create Propositions and queries | 2025-12-14 | 2025-12-15 |  | 1 day
100% | Final Recording | 2025-12-14 | 2025-12-16 |  | 2 days